## Development plan
[6 empty] | 30 martie | [6 empty] | 6 aprilie | [6 empty] | 13 aprilie | [6 empty] | 20 aprilie | [6 empty] | 27 aprilie | [6 empty] | 4 mai | [6 empty] | 11 mai | [6 empty] | 18 mai | [6 empty] | 25 mai | [6 empty] | 1 iunie
Task name | Start Date | End Date | Duration (hours) | Team member | Percent complete | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
[6 empty] | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D
PHASE 1 - Documentation & Research
Definirea tool-urilor folosite si a unei idei de baza a aplicatiei
Creare documentatie proiect | 2020-03-30 | 2020-06-01 |  | Ciucur Daniel | 30
Stabilire limbaj de programare, tool-uri … | 2020-03-30 | 2020-03-30 | 2 | TOTI | 100 | bar: Week 1 L
Creare document "riscuri" | 2020-04-01 | 2020-04-01 | 1 | Ciucur Daniel | 100 | bar: Week 1 M
Research si documentare pentru proiect
Documentatie C# back-end (ASP know-how) | 2020-04-07 | 2020-04-11 | 6 | Opra Andrei | 100 | bar: Week 2 M to Week 2 S
Creeare MockUp GUI al website-ului | 2020-04-08 | 2020-04-12 | 4 | Ciucur Daniel | 100 | bar: Week 2 M to Week 2 D
Erd schema pentru baza de date (initiala) | 2020-04-07 | 2020-04-12 | 8 | Iovescu Andrei, Tuns Adrian | 100 | bar: Week 2 M to Week 2 D
Creeare plan de proiect nou in excel | 2020-04-07 | 2020-04-07 | 4 | Ciucur Daniel | 100 | bar: Week 2 M
Document Requirements & High level analisys | 2020-04-24 | 2020-04-26 | 4 | TOTI | 0 | bar: Week 2 M; Week 4 V to Week 4 D
Prezentare demo C# in Visual Studio | 2020-04-13 | 2020-04-13 | 1 | Opra Andrei | 100 | bar: Week 3 L
PHASE 2 - Implementation
Sub-chapter
Database implementation
Initial database implementation | 2020-04-20 | 2020-04-21 | 4 | Iovescu Andrei,Tuns Adrian | bar: Week 4 L to Week 4 M
Populate database with data | 2020-04-21 | 2020-04-22 | 2 | Iovescu Andrei | 0 | bar: Week 4 M to Week 4 M
Basic UI functionality
Git Repository | 2020-04-23 | 2020-04-23 | 2 | TOTI | 100 | bar: Week 4 J
Implmentare UI initial | 2020-04-21 | 2020-04-29 | 10 | Opra Andrei | 100 | bar: Week 4 M to Week 5 M
Creeare branch pentru fiecare mebru | 2020-04-02 | 2020-04-02 | 3 | TOTI | 100 | bar: Week 5 S
Crearea server baza de date | 2020-04-02 | 2020-04-04 | 3 | Opra Andrei | 100 | bar: Week 5 S to Week 6 L
Implementare baza de date dupa schema | 2020-04-07 | 2020-04-08 | 3 | Iovescu Andrei, Tuns Adrian | 100 | bar: Week 2 M to Week 2 M
Implmentare EntityFramework in proiect | 2020-05-06 | 2020-05-07 | 5 | Iovescu Andrei | 100 | bar: Week 6 M to Week 6 J
Adaugare pagini in proiect dupa schema UI | 2020-05-07 | 2020-05-07 | 3 | Opra Andrei | 100 | bar: Week 6 J
Meeting pentru sincronizare | 2020-05-07 | 2020-05-07 | 5 | TOTI | 100 | bar: Week 6 J
Meniu manager | 2020-05-08 | 2020-05-10 | 5 | Ciucur Daniel | 100 | bar: Week 6 V to Week 6 D
Meniu programator | 2020-05-13 | 2020-05-14 | 5 | Opra Andrei | 100 | bar: Week 7 J to Week 7 V
LogIn page | 2020-05-08 | 2020-05-10 | 5 | Iovescu Andrei | 100 | bar: Week 6 V to Week 6 D
Styling login page | 2020-05-10 | 2020-05-10 | 5 | Iovescu Adrian | 100 | bar: Week 6 D
Create .gitignore and help team work with git | 2020-05-08 | 2020-05-08 | 2 | Tuns Adrian | 100 | bar: Week 6 V
Imbunatatire tabele | 2020-05-10 | 2020-05-12 | 5 | Tuns Adrian | 100 | bar: Week 6 D to Week 7 M
Add Edit, Delete functionality | 2020-05-13 | 2020-05-14 | 5 | Ciucur Daniel | 100 | bar: Week 7 J to Week 7 V
Fix errors with pages redirects | 2020-05-12 | 2020-05-12 | 2 | Ciucur Daniel | 100 | bar: Week 7 M
Adaugare functionalitate log in HttpSession | 2020-05-15 | 2020-05-18 | 5 | Iovescu Andrei | 100 | bar: Week 7 V to Week 8 L
Functionalitate de a schimba prima parola | 2020-05-18 | 2020-05-20 | 5 | Iovescu Andrei | 100 | bar: Week 8 L to Week 8 M
Styling manager si programator | 2020-05-15 | 2020-05-16 | 5 | Ciucur Daniel | 100 | bar: Week 7 V to Week 7 S
Imbunatatire arhitectura | 2020-05-15 | 2020-05-20 | 20 | TOTI | 100 | bar: Week 7 V to Week 8 M
Ecran programator |  |  | 5 | Opra Andrei | 100
Implementare ercan task programator | 2020-05-11 | 2020-05-15 | 15 | Opra Andrei | 100 | bar: Week 7 M to Week 7 S
Adaugare functionalitate AUTO ASIGN TASK | 2020-05-18 | 2020-05-20 | 10 | TOTI | 100 | bar: Week 8 L to Week 8 M
PHASE 3 - Testing
Sub-chapter
Testing- Debugging for potential errors | 2020-05-19 | 2020-05-23 | 10 | Tuns Adrian | 100 | bar: Week 8 M to Week 8 S
UI Adujustments | 2020-05-23 | 2020-05-25 | 5 | Ciucur Daniel | 100 | bar: Week 8 S to Week 9 L
PHASE 4 - Final phase
Documente
User manual | 2020-05-27 | 2020-05-28 | 4 | TOTI | 100 | bar: Week 9 M to Week 9 J
Prezentare Power Point | 2020-05-27 | 2020-05-29 | 2 | Ciucur Daniel | 100 | bar: Week 9 M to Week 9 V
Update al documentelor | 2020-05-29 | 2020-05-29 | 10 | TOTI | 100 | bar: Week 9 V

## Informatie de baza proiect
Nume: | Dispatcher
Functionlitate: | realizarea unui modul care sa imparta automat task-uri intr-o echipa
Platforma: | web app
Useri: | programatori respectiv managerii acestora
Limbaje de programare, librarii: | ASP .NET Core C#, HTML, CSS, JavaScript, SQL, BOOSTRAP
IDE, tools pentru development: | Visual Studio, MySQL Workbench, Lucid Chart
Tools pentru management: | Excel, Visual Paradigm, Google Suite, Discord for meetings, Creately
Dealine: | 5 iunie 2020

## Etape development
| Etape | Descriere etapa
1 | Documentare si Research | In aceasta etapa se va urmari: stabilirea idei de baza a proiectului, stabilirea technologiilor in care sa realizam proiectul, pregatirea unui plan de proiect, documentatii, etc. Toti membrii echipei vor consulta documentatii despre technologii tutoriale
2 | Implementare | Aceasta va fi etapa care va dura cel mai mult. Aici se va implementa baza de date, se va popula cu date. Se va implementa prototipul site-ului. Se vor adauga treptat functionalitatile. Iar in cele din urma se va efectua un styling al site-ului.
3 | Testing | Din prima mentionat, ca dupa fiecare feature adaugat, acesta trebuie testat imediat dupa ce a fost implementat. Dar vom avea si o etapa speciala dedica testarii integrale a proiectului de catre toti membrii.
4 | Faza de final a proiectului | In faza finala vom avea niste sloturi libere dedicate eventualelor riscuri nefinalizarea taskurilor, erori, etc. De asemenea in aceasta etapa se vor face ultimele modificari minimale aduse aplicatiei. In aceasta perioada se va realiza o prezentare ppt a aplicatiei si se vor finaliza toate documentele legate de proiect.
trht

## Echipa
Nume | Rol | Responsabilitati | Nr. ore/week
Ciucur Daniel | Team Leader | realizare plan de proiect si documentatii -arhitectura bazei de date si a aplicatiei -realizare meeting-uri (TeamLeader) implementare schelet front-end HTML si back-end C# implementarea bazei de date si a query-urilor pentru aceasta realizarea styling-ului aplicatiei si layout-ului in raport cu arhitectura, testing pe toata aplicatia | 5
Tuns Adrian | Programator |  | 5
Opra Andrei Radu | Programator |  | 5
Iovescu Adrei | Programator |  | 5